Part A
Course Introduction

---
https://twitter.com/WardCunningham/status/1469503516905336834

---
Part B
Project Management

---
SM
PO
SD
Product
Owner
Scrum
Master
Software
Developer

---
P
E
 3R
P
E
 3R
Sprint 1
Sprint n
time
Week 1
Week n
...
...
Mid-Project Release
Final Release
time
Sprints 1 to n/2
Sprints (n/2+1) to n

---
Process improvement
Product management
Software development
Daily Scrum
Retrospective
Release
Review
Process improvement
Product management
Software development
Daily Scrum
Next sprint
preparation
Process improvement
Product management
Software development
Daily Scrum
Process improvement
Product management
Software development
Sprint
planning
Wed
...
09:00
13:00
17:00
Tue
Mon
Thu

---
Awaiting review
Feature Archive
Product Backlog
In progress
Sprint Backlog
...
1. Tell-a-friend
2. Tell-a-friend
 Est. size = 8
6. Tell-a-friend
 Est. size = 8 Real size = 8
4. Tell-a-friend
 Est. size = 8
...
...
...
...
5. Tell-a-friend
 Est. size = 8 Real size = 8
3. Tell-a-friend
 Est. size = 8
...
...

---
...
...
5. Sprint Planning
6. Meeting After-work
1. Meeting Preparation
3. Sprint Release
4. Sprint Retrospective
2. Sprint Review
Team Meeting Day
Previous
Sprint
Next
Sprint
Team
Meeting

---
Product owner
picks feature
Product owner
reads story
Product owner
explains story
Developers
discuss story
Each developer
deliberates
Each developer
plays card
Agreement?
no
Product owner
adjusts backlog
Developers re-
view total effort
Done?
no
yes
yes
 start
end

---
Part C
Software Processes

---
Product
Management
Engineering
Quality
Assurance
MRD,
PRD
PM
EM
Rel.
Plan
Code
SD
EM
Code,
Script
QAE
Test
Plan
QAM
Plan
Code
Plan
Plan
Code

---
start
1st
release
incubate
develop
maintain
mature
retire
release
D
release
M
I

---
Quality
Scope
Time
Cost

---
start
end
time
    Planning
        Review
        Release
     Execution
6 months – 5 years

---
time
...
P
E
 3R
P
E
 3R
P
E
 3R
Iteration n-1
Iteration n+1
Iteration n
...
1-4 weeks
1-4 weeks
1-4 weeks

---
S1
T1
T2
T3
T4
T5
S5
S3
S2
S1
T1
T2
T3
T4
T5
S4
S5

---
time
Plan-driven methods
Long iterations
time
Agile methods
Short iterations

---
Feature 1
Feature n
Feature 2
Feature 1
Feature n
Feature 2
Feature 1
Feature n
Feature 2
User interface
Persistence layer
Domain model
Business domains
Technical domains

---
Open source
Company
 Agile Methods
 Not differentiating
 Competitively differentiating
Product 1
Feature 1
Feature n
Feature 2
Product n
Feature 1
Feature n
Feature 2
Product 2
Feature 1
Feature n
Feature 2
User interface
Domain model
Persistence layer
 Inner Source
 Open Source

---
time
...
P
E
 3R
P
E
 3R
P
E
 3R
Sprint n-1
Sprint n+1
Sprint n
...
1-4 weeks
1-4 weeks
1-4 weeks
time
6-12 months
6-12 months
6-12 months
   Rel. m-1
   Rel. m
   Rel. m+1
...

---
SD
SD
PM
SD
...
PM
EM
SD
SD
SD

---
P
...
...
time
3R
E

---
Part D
Product Management

---
Backlog Item
Theme
Feature
User Story
Epic
Refactoring
Bug Report

---
<system>
“could”
“should”
“must”
“allow for”
“be able to”
“...”
<activity>
<object>

---
value
realize
second
realize
first
realize
never
2
3
x
1
realize
last
risk
high
risk
low
high
value
low

---
high
customer satis-faction
low
fully
degree of feature
implementation
not at all
exciters and
delighters
must-have
linear

---
time
...
P
E
 3R
P
E
 3R
P
E
 3R
Sprint n-1
Sprint n+1
Sprint n
...
1-4 weeks
1-4 weeks
1-4 weeks
time
6-12 months
6-12 months
6-12 months
   Rel. m-1
   Rel. m
   Rel. m+1
...
...
time
2014-04-01
2015-04-01
2014-10-01
...
Release 1.3
New functionality
Release 2.1
Major bug fixes
Release 2.0
New architecture
...

---
time
...
P
E
 3R
...
  Expo
...
time
...
P
E
 3R
...
...
P
E
 3R
  Release

---
Part E
Software Development

---
Refactor
Add Function
code smells
code does not
smell anymore

---
Part F
Quality Assurance

---
implementation
test suite
feature
4
1
2
3
6
5

---
...
feature n+2
feature n+1
feature n-1
feature n-2
test suite n-1
test suite n-2
implementation n-1
implementation n-2
...
...
...
on to next feature
feature n
implementation n
test suite n
enhance test suite

---
edit
compile
build
test
deploy
deploy
edit
compile
build
deploy
commit
Developer
Environment
Production
System
operate
test
build

---
build
deploy
test
edit
compile
build
deploy
commit
Developer
Environment
Test
System
fetch
Production
System
deploy
operate
test
release
build
fetch
monitor

---
Part G
Process Improvement

---
Release
Release
Retro-
spective
P
E
 3R
Project
Retro-
spective
Release Scope
Sprint Scope
Project
Scope