Project Setup
Prof. Dr. Dirk Riehle
Friedrich-Alexander University Erlangen-Nürnberg
AMOS A02
Licensed under CC BY 4.0 International

---
Agenda
1. Code repository
2. Issues
3. Project board
4. Committing code
5. Planning documents
6. Impediments backlog
7. Weekly checklist

---
Project Management
- The AMOS Project directive is simplify, simplify, simplify!
  - GitHub repository, issues, and project board for software development
  - Google Sheets for high-level product and process management
  - Teams may add additional tools at their discretion (and own risk)

---
The Wahlzeit / Flowers Example

---
1. Code Repository

---
GitHub Code Repository Set-up
- GitHub account
  - Please create a GitHub account if you don’t have one yet
  - Add your account name (handle) to planning documents
- GitHub project
  - We will create a team for you and invite you to a code repository
  - You will all be owners of the code repository, initially; change as you see fit
- Your project name will be amosproj / amos2021ws0x-fabulous-project
  - It will be public (read access to world)
  - It uses the MIT license
- You can collaborate as you see fit (but should agree first)
  - For grading, we will look at the above project

---
License and Copyright Declaration
Please use the REUSE SOFTWARE [1] format to declare license and copyright in files
// SPDX-License-Identifier: MIT
// SDPX-FileCopyrightText: 2010-2021 Dirk Riehle <dirk@riehle.org>
// SPDX-FileCopyrightText: 2019 Georg Schwarz <georg.schwarz@fau.de>
[1] See https://reuse.software/

---
2. Issues

---
Feature and User Story
- Definition of feature
  - A distinguishing characteristic of a software item (for example, performance, portability, functionality)
    (IEEE 829)
- Definition of user story
  - A description mechanism for a software feature used to create a shared understanding of the feature; follows an established pattern
  - The description pattern is: As a “user role”, I need “a function”, so that “I get business value” where the parts in quotation marks are substituted
- Example user stories
  - Rate-a-photo: As a visitor, I can rate a photo with a numerical value 1-10, so that I can share my opinion about the photo.
  - Tell-a-friend: As a user, I need a function to tell a friend about a flower photo, so that I can share my passion for flowers.

---
Types of Issues
- Features
  - New functional improvements
- Refactorings
  - Behavior-preserving improvements
- Bugs
  - Fixes to malfunctioning

---
Quality Criteria for Features
I	ndependent: Features should be independent of each other.
N	egotiable: A feature is man-made, not cast in stone.
V	aluable: Every feature should have business value.
E	stimatable: A feature should be precise so that size can be estimated.
S	mall: A feature should be small enough for one iteration.
T	estable: A feature should have testable success criteria.

---
GitHub Issues Set-up
- GitHub issue template
  - Please create a template for feature requests
  - The template should contain fields for
    - Short name (already preset as title field)
    - Short description (using user story)
    - Acceptance criteria (to test for fulfillment)
    - Definition of done (from week 5 on)
- Create labels for features sizes
  - Est. size = X for estimated sizes
    - Set during sprint planning
  - Real size = Y for actual size
    - Set during sprint review
  - Use escalating colors
- Feel free to add more templates

---
The Tell a Friend Feature 1 / 2

---
The Tell a Friend Feature 2 / 2

---
3. Project Board

---
The Feature Life-Cycle
Awaiting review
Feature Archive
Product Backlog
In progress
Sprint Backlog
...
1. Tell-a-friend
2. Tell-a-friend
 Est. size = 8
6. Tell-a-friend
 Est. size = 8 Real size = 8
4. Tell-a-friend
 Est. size = 8
...
...
...
...
5. Tell-a-friend
 Est. size = 8 Real size = 8
3. Tell-a-friend
 Est. size = 8
...
...

---
Product Backlog and Product Backlog Entry
- Product backlog entry
  - A named, identifiable, and prioritized feature, bug, or refactoring
- Product backlog
  - An incomplete, evolving list of features prioritized by business value
- Purpose of product backlog
  - To know what’s coming up next

---
Sprint Backlog and Sprint Backlog Entry
- Sprint backlog entry
  - A high-quality product backlog entry that
    - has been estimated for size and committed-to to being implemented by the software developers
- Sprint backlog
  - A list of sprint backlog entries that
    - the software developers have committed to implementing in the current sprint
- Purpose of sprint backlog
  - To know at any time what to do in the current sprint
  - To serve for task allocation between developers

---
Feature Archive
- Feature archive
  - All issues that have been implemented
  - All issues contain the original size estimation
  - All issues contain the real (after-implementation) size
- Purpose of feature archive
  - To serve as a summary of product features
  - To allow lookup of history of development

---
GitHub Project Set-up
- GitHub project
  - Please create a project (board) for backlogs
  - The board should have five columns
    1. Product backlog (for new unscheduled features)
    2. Sprint backlog (for features to-be-done)
    3. In progress (for features currently in work)
    4. Awaiting review (for features to be reviewed)
    5. Feature archive (for finished features)
- Connect issues with project

---
The Wahlzeit / Flowers Project Board

---
Task Planning / Assigning Backlog Entries

---
4. Committing Code

---
Use Only One Account Per Student
- Please use only one account, the one you list in the planning documents
  - If you find that you used multiple accounts, please tell us about it

---
Identify Co-authors When Pair Programming
- If you are pair programming, give credit when committing
  - Add trailing Co-authored-by to commit message
  - Use your GitHub no-reply email address if you want to keep your email private
dirk@host$ git commit -a -m "Fixed problem Co-authored-by stefan-buchner@users.noreply.github.com"

---
5. Planning Documents

---
Planning Documents Set-up
- Strategic planning uses Google Sheets
  - We will share a folder with the planning documents with you
  - Please check everyone has access
- Wahlzeit / Flowers example
  - Planning artifacts: http://bit.ly/3qitBF1

---
Planning Documents
#	Artifact Name	Artifact Purpose
1	Project data	Provides basic project data
2	Project team	Shows project team and static roles, if any
3	Team contract	Shows team contract
4	Role assignments	Tracks role assignment
5	Product goal	Proides product vision and project mission
6	Product glossary	Provides domain terminology of project
7	Mid-project release tracking	Tracks mid-project release sprints
8	Final project release tracking	Plans and tracks final project release sprints
10	Definition of done	Provides decision criteria for “done”
11	Documentation	Provide links to documentation of product
12	Bill of materials	Lists all third-party components
13	Planning poker	Provides simple tool for planning poker

---
1. Project Data

---
1. Project Data (Explanation)
- Definition
  - A collection of relevant (starting point) links
- Purpose
  - To simplify navigation
- Production and system
  - Deployment scenarios depend on project
- GitHub repository
  - Required
- CI tooling
  - Optional

---
2. Project Team

---
2. Project Team (Explanation)
- Definition
  - The list of team members and their contact information
- Purpose
  - To make it easy to contact individuals or the whole team
- Pragmatics
  - Feel free to add other information, e.g. Skype ID

---
3. Team Contract

---
3. Team Contract (Explanation) [1]
- Definition
  - A uniform agreement of the team as to which goals, norms, rewards, and sanctions they play by
- Purpose
  - To have a defined and agreed-upon way of operating as a team
[1]	https://oss.cs.fau.de/teaching/course-resources/student-team-contract/

---
4. Role Assignments

---
4. Role Assignments (Explanation)
- Definition
  - A week-by-week assignment of roles to team members
- Purpose
  - To have a plan and history of role assignments so everyone knows their job
- Pragmatics
  - Please plan out the project at start of course
  - Feel free to add roles beyond the four required ones
- Use the same week numbers as in the Course schedule
  - Week 1 starts with the first lecture
  - Week 1 also starts the first sprint

---
5. Product Goal

---
5. Product Goal (Vision and Mission)
- Definition of product vision
  - A product vision communicates
    - The main purpose and core functionality of the product
    - The value the main stakeholders receive
  - It is inspiring, timeless, focused and the final arbiter
- Definition of project mission
  - A project mission summarizes
    - What the project wants to achieve
    - Within the project time-frame
- Purpose
  - To succinctly explain product and project
  - To guide when prioritizing features

---
6. Product Glossary

---
6. Product Glossary (Explanation)
- Definition
  - Is an alphabetically ordered list of terms and their definition
- Purpose
  - To provide key domain terminology (shared vocabulary) of project
  - Is a simplified form of a domain model accessible to everyone
- Term
  - A (possibly qualified) noun determining the concept to be defined
- Term definition
  - The definition of the referenced term
  - A base definition is a declarative statement of the form X is a X*
  - Other forms of definitions are synonyms, short-hands, etc.

---
7. Mid-Project Release Tracking

---
7. Mid-Project Release Tracking (Explanation)
- Definition
  - A prioritized list of features for a product release
- Purpose
  - To predict the content of the upcoming product release
- Pragmatics
  - Has been estimated by developers, validated by historic data
  - Is a living document, that is, gets adjusted after each sprint

---
8. Final Project Release Planning and Tracking

---
8. Final Project Release Planning and Tracking (Explanation)
Like mid-project release tracking, but with added planning

---
10. Definition of Done

---
10. Definition of Done (Explanation)
- Definition
  - Is a check list of decision criteria to determine status of “done”
- Purpose
  - To be consistent about what “done” means
- Pragmatics
  - Definitions of “done” (DoD) require team consensus
  - There are many such decisions, hence many DoDs needed
  - At a minimum, at the proper time, the team should have a
    - DoD for features
    - DoD for sprint release
    - DoD for product release

---
11. Documentation

---
11. Documentation (Explanation)
- Definition
  - The product documentation (where to find what)

---
12. Bill of Materials

---
12. Bill of Materials (Explanation)
- Definition
  - A list of items (“materials”) included in the project
  - Items typically mean open source libraries
- Purpose
  - To maintain an overview of “what’s the box”
- Pragmatics
  - Please lists all third-party components used by the product
  - List only those used directly; no need to recursively unpack
  - In case of open source components, also list their license

---
13. Planning Poker

---
6. Impediments Backlog

---
9. Impediments Backlog

---
9. Impediments Backlog (Explanation)
- Definition
  - A list of current and historic impediments to process
- Purpose
  - To know at any time the current impediments
  - To see whether any impediments keep recurring
- Pragmatics
  - It names the Scrum master responsible for resolution
  - It provides the solution found, if any

---
7. Weekly Checklist

---
Weekly Checklist for Artifacts
- Software product
  - Tagged, testable, deployable software code base and product
- Planning documents
  - Clean project board, release planning, additional information
- Process improvement
  - Impediments documented; happiness index survey taken

---
Summary
1. Code repository
2. Issues
3. Project board
4. Committing code
5. Planning documents
6. Impediments backlog
7. Weekly checklist

---
Thank you! Questions?
dirk.riehle@fau.de – https://oss.cs.fau.dedirk@riehle.org – https://dirkriehle.com – @dirkriehle
DR

---
Legal Notices
- License
  - Licensed under the CC BY 4.0 International license
- Copyright
  - © 2010-2021 Dirk Riehle, some rights reserved