The Team Meeting
Prof. Dr. Dirk Riehle
Friedrich-Alexander University Erlangen-Nürnberg
AMOS B02
Licensed under CC BY 4.0 International
[Speaker Notes: It is Friedrich-Alexander University Erlangen-Nürnberg – FAU, in short. Corporate identity wants us to say “Friedrich-Alexander University”.]

---
The Scrum Sprint (Recap)
Process improvement
Product management
Software development
Daily Scrum
Retrospective
Release
Review
Process improvement
Product management
Software development
Daily Scrum
Next sprint
preparation
Process improvement
Product management
Software development
Daily Scrum
Process improvement
Product management
Software development
Sprint
planning
Wed
...
09:00
13:00
17:00
Tue
Mon
Thu

---
The AMOS Team Meeting
...
...
5. Sprint Planning
6. Meeting After-work
1. Meeting Preparation
3. Sprint Release
4. Sprint Retrospective
2. Sprint Review
Team Meeting Day
Previous
Sprint
Next
Sprint
Team
Meeting

---
1. Meeting Preparation
This sprint’s release manager
  1. Ensure that a working demo system will be available
  2. Tag release candidate with sprint-xx-release-candidate
    - where xx is your sprint number (see project schedule)
- The next sprint’s product owner
  - Ensure that product backlog is ready for sprint planning
    - Include new feature requests
    - May include bugs as issues
    - May include refactorings
  - This should be done in a next sprint preparation meeting

---
2a. Sprint Review
This sprint’s release manager
  1. Check-out fresh code base using release candidate tag
  2. Compile, build, and run tests for release candidate
  3. Deploy release candidate to test environment
The release manager does not run the review

---
2b. Sprint Review
- This sprint’s product owner
  - Walk through sprint backlog feature by feature
    1. Ask developer to demo current feature under review
    2. Check fulfillment of acceptance criteria
    3. Check fulfillment of definition of done, if required
    4. Check other criteria incl. logging output for problems
    5. If successfully implemented, move feature to feature archive
    6. If not successfully implemented, move feature back to product backlog
- Software developer
  1. Demo feature as requested by product owner
  2. Answer questions about feature design and implementation
  3. Provide real size as determined after implementation

---
Kanban Board and Feature Life-Cycle
Awaiting review
Feature Archive
Product Backlog
In progress
Sprint Backlog
...
1. Tell-a-friend
2. Tell-a-friend
 Est. size = 8
6. Tell-a-friend
 Est. size = 8 Real size = 8
4. Tell-a-friend
 Est. size = 8
...
...
...
...
5. Tell-a-friend
 Est. size = 8 Real size = 8
3. Tell-a-friend
 Est. size = 8
...
...

---
3. Sprint Release
- This sprint’s product owner
  - Decide whether release candidate should be released
    - Only in case of significant regression should you not release
  - Consult with software developers if necessary
- This sprint’s release manager
  - If the release candidate is to be released
    1. Deploy sprint release to operations environment
    2. Tag release with sprint-xx-release where xx is your sprint number
  - If you maintain a change log (optional)
    - Update change log with release information

---
4. Sprint Retrospective
This sprint’s Scrum master
  - Review this sprint’s impediments
    - Report on progress
    - Review remaining problems
Next sprint’s Scrum master
  - Make roll call as to new impediments
    - Take note of people's impediments
    - Allow everyone to make a suggestion
  - Note impediments in impediments backlog
Everyone
  - Answer to happiness index

---
Happiness Index

---
5. Sprint Planning
This (now new) sprint’s product owner
  1. Reprioritize backlog items, if necessary, on-the-fly
  2. Work through top-prioritized backlog items one-by-one until finished
    - For each product backlog item, explain it, ask developers to estimate and commit
    - You are finished, if the team does not want to take on more backlog items
- Software developer
  - Estimate size of each backlog item using planning poker
  - After planning, commit to backlog items put into sprint backlog
- Everyone
  - Make sure roles for sprint are clear to everyone

---
Story Points
- Story point
  - An arbitrary numeric measure of size of a given feature
- Properties
  - Is a measure of size, not of effort or duration
  - Measured in non-linear increments, forcing choice
  - Is socially agreed upon, depends on team estimation history
  - Is independent of a particular person (and their skills)
  - Is mapped to time using the team's velocity (development speed)
Points	Meaning
0	No size
1	Trivial size
2	Small size
3	Medium size
5	Large size
8	Very large size
13	Too large (size)

---
Flow Diagram for Sprint Planning [1]
[1]	A simple planning poker cards replacement can be found in the planning documents
Product owner
picks feature
Product owner
reads story
Product owner
explains story
Developers
discuss story
Each developer
deliberates
Each developer
plays card
Agreement?
no
Product owner
adjusts backlog
Developers re-
view total effort
Done?
no
yes
yes
 start
end

---
6. Meeting After-work
- This sprint’s product owner
  - Update planning documents to consistent state
    - Clean up product and sprint backlog
    - Ensure feature archive is current
    - Update release plan with actual effort for sprint
- Software developers
  - Plan programming tasks (1 feature = 1+ tasks)
    - Agree on which developer(s) work(s) on which tasks
    - If pair programming, ensure you document the pair
    - May happen right after meeting or during sprint
- This sprint’s Scrum master
  - Work on resolving impediments during sprint
  - Document resolutions in impediments backlog

---
Thank you! Questions?
dirk.riehle@fau.de – https://oss.cs.fau.dedirk@riehle.org – https://dirkriehle.com – @dirkriehle
DR

---
Legal Notices
- License
  - Licensed under the CC BY 4.0 International license
- Copyright
  - © 2010-2021 Dirk Riehle, some rights reserved