Scrum Overview
Prof. Dr. Dirk Riehle
Friedrich-Alexander University Erlangen-Nürnberg
AMOS C03
Licensed under CC BY 4.0 International
[Speaker Notes: It is Friedrich-Alexander University Erlangen-Nürnberg – FAU, in short. Corporate identity wants us to say “Friedrich-Alexander University”.]

---
Agenda
1. Scrum overview
2. Product owner
3. Software developer
4. Scrum master
5. Core activities

---
Principles of the Agile Manifesto [A01]
Individuals and Interactions
(over Processes and Tools)
Working Software
(over Comprehensive Documentation)
Customer Collaboration
(over Contract Negotiation)
Responding to Change
(over Following a Plan)

---
Process and Technical Practices
Scrum
(for process practices)
XP
(for technical practices)

---
1. Scrum Overview

---
Scrum Definition 1 / 2
- An agile method, invented around 1993, 1995
- A rugby situation requiring intense collaboration

---
Scrum Definition 2 / 2 [S04] [C06]
- A (minimal) agile process model
- Independent of software development
- Where definitions sometimes vary (two fathers)

---
Scrum Process Scope
Portfolio
Product
Release
Sprint
Day

---
Scrum Process Overview
P:	Planning
E:	Execution
3R:	Review, release, and retrospective
time
...
P
E
 3R
P
E
 3R
P
E
 3R
Sprint n-1
Sprint n+1
Sprint n
...
1-4 weeks
1-4 weeks
1-4 weeks
time
6-12 months
6-12 months
6-12 months
   Rel. m-1
   Rel. m
   Rel. m+1
...

---
Scrum Roles, Practices, and Artifacts
[1]	Originally “team members”
Product owner
Software developer [1]
Scrum master
PO
Roles
Product backlog
Sprint backlog
Burndown chart
...
Product
Backlog
Artifacts
Sprint planning
Daily Scrum
Sprint review
Release planning
…
Perform
Daily
Scrum
Practices

---
Scrum Roles and Responsibilities
SM
PO
SD
Product
Owner
Scrum
Master
Software
Developer

---
Committed vs. Involved (Scrum Lore)
- Committed
  - Product owner
  - Software developer
  - Scrum master
- Involved
  - Customer
  - Marketing manager
  - Sponsor / funder
  - Others ...

---
2. Product Owner

---
Product Owner
- Holds overall responsibility for the product being developed
- Provides
  - product vision,
  - product requirements
- Plans and helps plan development
- Tracks progress

---
Product Owner Responsibilities
Opportunity Assessment
Product Specification
Development Planning
Progress Tracking

---
Traditional to Scrum Role Mapping (Recap)
Traditional
Scrum
Product Manager
Product Owner
Engineering Manager
Software Developer
Software Developer
Scrum Master
QA Engineer

---
Product Owner Processes and Artifacts
Processes	Artifacts
Opportunity Assessment	Product Vision
Product Specification	Product Glossary / Product Backlog / Feature Archive
Product Planning	Sprint Backlog / Release Plan
Progress Tracking	Burndown Charts / Feature Archive

---
Traditional vs. Scrum Product Management
- Traditional Product Manager
  - Product manager is responsible for product strategy and specification
  - Product manager does not interfere with detail development planning
  - Product Manager is frequently high-level, delegates product decisions to engineering
- Scrum Product Owner
  - Product owner is also responsible for product strategy and specification
  - Product owner shoulders some of the engineering manager role
  - Product owner is very much in the details of planning and tracking development
Scrum is a framework and thus typically
enhanced with other roles and responsibilities

---
3. Software Developer

---
Software Development Team
- Holds overall responsibility for delivering working software
  - That provides the features the team committed to delivering

---
Software Developer Responsibilities
Architecture Definition
Feature Implementation
Size Estimation
Sprint Commitment

---
Traditional to Scrum Role Mapping (Recap)
Traditional
Scrum
Product Manager
Product Owner
Engineering Manager
Software Developer
Software Developer
Scrum Master
QA Engineer

---
Software Developer Processes and Artifacts
Processes	Artifacts
Development Planning	Sprint Backlog
Software Development	Software
Quality Assurance	Software

---
4. Scrum Master

---
Scrum Master
- Holds overall responsibility for
  - Removing non-technical obstacles from the project’s path

---
Traditional to Scrum Role Mapping (Recap)
Traditional
Scrum
Product Manager
Product Owner
Engineering Manager
Software Developer
Software Developer
Scrum Master
QA Engineer

---
Scrum Master Processes and Artifacts
Processes	Artifacts
Process Facilitiation	Impediment Backlog
Process Improvement	Impediment Backlog

---
Line Reporting (vs. Roles)
PM	Product Manager
EM	Engineering Manager
SD	Software Developer
SD
SD
PM
SD
...
PM
EM
SD
SD
SD

---
5. Core Activities

---
Scrum Sprints (Iteration)
- A sprint is Scrum's iteration; it is an equal-length time-box
- It is a highly structured process with defined feedback points
P:	Planning
E:	Execution
3R:	Review, release, and retrospective
P
...
...
time
3R
E

---
Sprint Structure
Process improvement
Product management
Software development
Daily Scrum
Retrospective
Release
Review
Process improvement
Product management
Software development
Daily Scrum
Next sprint
preparation
Process improvement
Product management
Software development
Daily Scrum
Process improvement
Product management
Software development
Sprint
planning
Wed
...
09:00
13:00
17:00
Tue
Mon
Thu

---
Main Work Streams of Sprints
Product management
(Product owner)
Software development
(Software developer)
Process improvement
(Scrum master)

---
Sprint Planning
- Definition
  - Serves to plan the upcoming sprint’s work
  - Involves product owner, software developers, and Scrum master
  - Results in sprint backlog containing the upcoming sprint’s work
- Activities
  - Product owner
    - The product owner provides the prioritized list of features
  - Software developer
    - The software developers estimate feature size using planning poker
    - Features keep being added to sprint backlog until there is enough work
    - Software developers breakdown features into tasks, distribute them
  - Scrum master
    - Observes team dynamics

---
Sprint Execution
- Definition
  - Serves to evolve product
- Activities
  - Product owner
    - Answers developer questions about features
    - Evolves product backlog, updates release plan
  - Software developer
    - Implement features from sprint backlog
    - Interact with product owner to refine feature specifications
  - Scrum master
    - Learns about process impediments
    - Tries to fix those impediments

---
Next Sprint Preparation
- Definition
  - Serves to prepare the upcoming sprint planning meeting
  - Involves product owner and at least one software developer
  - Results in sufficiently comprehensive product backlog
- Activities
  - Product owner
    - The product owner provides the prioritized list of features
    - Includes high-priority bug reports as backlog entries
  - Software developer
    - Provides size estimates for highly prioritized features
    - Adds refactorings for planning consideration

---
Sprint Review, Release, and Retrospective
- Definition
  - Sprint review
    - Product owner reviews results
    - Team signs off on finished features
  - Sprint release
    - Stakeholders sign off
    - If so, product is released
  - Sprint retrospective
    - Team reviews process
    - Developers commit to improvements

---
Review / Summary of Session
- Scrum defined
  - Scrum process overview and scope
  - Scrum roles, activities, and artifacts
  - When compared with traditional definitions

---
Thank you! Questions?
dirk.riehle@fau.de – http://osr.cs.fau.de
dirk@riehle.org – http://dirkriehle.com – @dirkriehle
DR

---
Credits and License
- Original version
  - © 2021 Dirk Riehle, some rights reserved
  - Licensed under Creative Commons Attribution 4.0 International License
- Contributions
  - None yet