Planning and Tracking
Prof. Dr. Dirk Riehle
Friedrich-Alexander University Erlangen-Nürnberg
AMOS D02
Licensed under CC BY 4.0 International
[Speaker Notes: It is Friedrich-Alexander University Erlangen-Nürnberg – FAU, in short. Corporate identity wants us to say “Friedrich-Alexander University”.]

---
Cartoon Lesson
- Software developers are optimists
- Reliable prediction is difficult
- You are always 80% there

---
Product Planning (Practices)
Roadmapping
Release planning
Sprint planning
Feature planning

---
Roadmap (On-going)
time
...
P
E
 3R
P
E
 3R
P
E
 3R
Sprint n-1
Sprint n+1
Sprint n
...
1-4 weeks
1-4 weeks
1-4 weeks
time
6-12 months
6-12 months
6-12 months
   Rel. m-1
   Rel. m
   Rel. m+1
...
...
time
2014-04-01
2015-04-01
2014-10-01
...
Release 1.3
New functionality
Release 2.1
Major bug fixes
Release 2.0
New architecture
...

---
Relationship between Planning Horizons
- A roadmap is a sequence of releases
  - A roadmap can stretch over multiple years
- A product release is a sequence of sprints
  - A product release can take anything from 3-12 months or more
- A sprint is a (short) time-box / iteration
  - A sprint can be anything from 1-4 weeks

---
Definition of Done (Artifact)
- Definition of Done (DoD)
  - An auditable check-list of results
  - Built from value-adding activities
  - That everyone previously agreed to
- Other properties
  - Should be orthogonal to acceptance criteria
  - It is about the non-functional aspects of work

---
Definition of Done (Practices)
- Agree on Definition of Done
  - Responsible: Product owner, developers
  - Artifacts: Definition of Done
  - Collaborators: Same
- Apply Definition of Done
  - Responsible: Product owner, developers
  - Artifacts: Definition of Done
  - Collaborators: Same

---
Applicability of Definition of Done
Product Release
Sprint Release
Single Feature

---
Example DoD for Single Feature
- Single feature DoD
  - Unit tests for feature have been written and are passing
  - Code review has been completed
  - Feature branch has been tagged and merged
- Always expected
  - Project builds, deploys, and tests successfully
  - Feature was demoed and accepted by product owner

---
Definition of Done vs. Acceptance Criteria
- DoD (Feature)
  - The same for every entry
- Acceptance Criteria
  - Specific to a backlog entry

---
Types of Sprints
Regular sprint
Exploratory sprint
Cleanup sprint
Release sprint

---
Start and Duration of Regular Sprints
- Monthly Sprints
  - Is original recommendation
  - Is too long for some domains
  - Should start 1st Monday
- Two Week Sprints
  - Are realistic even for beginners
  - Align with half-month rhythm
  - Should start on Wed or Thu
- One Week Sprints
  - Requires well-working team
  - Are needed in some domains
  - Should start on Wed or Thu

---
Irregular Sprints
time
...
P
E
 3R
...
  Expo
...
time
...
P
E
 3R
...
...
P
E
 3R
  Release

---
Quiz: Working with Time 1 / 2
Your startup is selling designer clothes to consumers on the web. What sprint duration should you choose?
  1. 1 week sprints
  2. 4 week sprints
Your startup is selling cryptography software to enterprise customers. What sprint duration should you choose?
  1. 1 week sprints
  2. 4 week sprints

---
Quiz: Working with Time 2 / 2
Your consulting firm is hired to enhance a bank’s email software with a cryptography plug-in. Should you suggest a
  1. Defined scope but no deadline
  2. Project deadline (fixed release date)
You are coordinating the development of an open source multi-component JEE platform implementation. Should you release
  1. When a defined scope is reached
  2. When a defined date is reached

---
Sprint Planning 1 / 3 (Practices)
- Prepare Sprint Planning Meeting
  - Responsible: Product owner
  - Artifacts: Features, product backlog
  - Collaborators: Developers

---
Sprint Planning 2 / 3 (Practices)
- Lead Sprint Planning Meeting
  - Responsible: Product owner / Scrum master
  - Artifact: Product and sprint backlog
  - Collaborators: Developers
- Explain Feature
  - Responsible: Product owner
  - Artifact: Feature
  - Collaborators: Developers
- Estimate Feature Size (a.k.a. Play Planning Poker)
  - Responsible: Developers
  - Artifact: Feature
  - Collaborators: Product owner

---
Playing Planning Poker (Practice)
Product owner
picks feature
Product owner
reads story
Product owner
explains story
Developers
discuss story
Each developer
deliberates
Each developer
plays card
Agreement?
no
Product owner
adjusts backlog
Developers re-
view total effort
Done?
no
yes
yes
 start
end

---
Sprint Planning 3 / 3 (Practices)
- Manage Sprint Backlog
  - Responsible: Product owner
  - Artifacts: Features, product and sprint backlog
  - Collaborators: Developers

---
Sprint Backlog (Artifact)

---
Example DoD for Sprint Release
- Sprint Release DoD
  - Database consistency checks in test environment succeeded
- Always expected
  - Project builds, deploys, and tests successfully

---
Quiz: Sprint Planning
If a “user registration feature” is 8 story points, then a “user login feature” must be of size
  1. Less than 8 points
  2. Exactly 8 points
  3. More than 8 points
  4. Cannot determine

---
Development Speed (Velocity)
v = s / t
[ story points / sprint ]
v	=	speed (velocity)
s	=	size (of feature)
t	=	time (in sprints)

---
Track Development Speed (Practice)
- Track Development Speed
  - Responsible: Product owner
  - Artifacts: Sprint backlog
  - Collaborators: None

---
Development Speed Chart (Artifact)

---
Working with Development Speed

---
Quiz: Progress Tracking
You are calculating development speed using a moving average of the last four sprints. Development speed fluctuates wildly. Possible reasons may be:
  1. The user stories are badly written
  2. The team is being distracted
  3. The code quality is poor
  4. All of the above

---
Release Planning (Practice)
- Plan Releases
  - Responsible: Product owner
  - Artifacts: Release plan
  - Collaborators: Market / customer, funder / sponsor
  - Note: Not part of Scrum proper

---
Release Plan (Artifact)
- Release Plan
  - A sequence of releases with defined start and end times
  - Where each release represents a deployable product increment
  - That provides new significant business value to market / customer
  - Note: Core of roadmap is captured as the release plan
- Other properties
  - Defined rhythm: Releases should be of about equal length in time
    - Common are 3, 6, and 12 months increments
  - External factors: Start and end dates are often determined by external factors
- The release plan defines the release schedule

---
Example Release Plan

---
Release as Sequence of Sprints
time
...
P
E
 3R
P
E
 3R
P
E
 3R
Sprint n-1
Sprint n+1
Sprint n
...
1-4 weeks
1-4 weeks
1-4 weeks
time
6-12 months
6-12 months
6-12 months
   Rel. m-1
   Rel. m
   Rel. m+1
...

---
Single Release Plan (Artifact)
- Single Release Plan
  - Is a product increment for the next market release / customer deployment
  - Consists of all product backlog items considered part of that increment
  - Structures the release into sprints by theme and purpose
  - Is a planning and communication tool, not a strict plan
- Other properties
  - Evolving: Is adapted in reaction to changes in team and environment

---
Single Release Planning (Practice)
- Plan Single Release
  - Responsible: Product owner
  - Artifacts: Single release plan
  - Collaborators: Market / customer, developers

---
Example DoD for Product Release
- Product release DoD
  - Component test coverage is 70% or higher
  - Software documentation passes external review
  - User manual passes external review
- Always expected
  - Project builds, deploys, and tests successfully

---
Track Release Burn-Down
- Track Release Burn-down
  - Responsible: Product owner
  - Artifacts: Release burn-down chart
  - Collaborators: None

---
Release Burndown Chart (Artifact)

---
Predicting Burn-down

---
Adjusting Burn-down

---
Roadmap (Artifact)
- External Roadmap
  - Overview-oriented; few details are provided
  - Serves communication needs
  - Serves external stakeholders
- Internal Roadmap
  - As detail oriented as needed (richer than external roadmap)
  - Serves planning and communication needs
  - Serves internal stakeholders

---
Roadmap as Sequence of Releases
External roadmap
Internal roadmap
time
6-12 months
6-12 months
6-12 months
   Rel. m-1
   Rel. m
   Rel. m+1
...
...
time
2014-04-01
2015-04-01
2014-10-01
...
Release 1.3
New functionality
Release 2.1
Major bug fixes
Release 2.0
New architecture
...

---
Roadmapping (Practice)
- Plan Roadmap
  - Responsible: Product owner
  - Artifacts: Release plan, releases
  - Collaborators: Market / customer, funder / sponsor
  - Note: Not part of Scrum proper

---
Example Roadmap
time
start
2011-07-13
2012-03-30
alpha
2012-05-30
beta
2012-07-30
GA
Minimal Product
Runs on Linux Stack
Deployable at Cust#1 Site
alpha
+ QA
beta
+ QA
Funding
Review
time
2013-01-15
v2.2
2013-07-15
v2.3
2014-01-15
v2.4
Integrates wazoo
Allows humpling
Runs on Windows
Meets accessibility reqs
Single-click installer
Meets new perf. reqs
Dingsbums compatible
CES
CES

---
Vision vs. Roadmap vs. Release
	Timeframe	Content	Certainty	Owner
Product / Vision	Long-term / (3+ years)	High-level ideas	Low	CEO
Product / Roadmap	Medium (1-5 years)	Themes and epics	Medium	Strategic product manager
Product / Release	Short-term (months)	Epics and features	High	Technical product manager

---
Planning by Organizational Scope
Quarterly
goals
Quarterly
goals
Sprint planning
Release planning
Roadmapping
Annual goals
Annual goals
time scope
Organizational Scope
Team / Product
Department / Portfolio
Company

---
Review / Summary of Session
- Scrum planning and tracking
  - Scopes and time-horizons
  - Definition-of-done (vs. acceptance criteria)
- Sprints and sprint planning
  - Definition and types of sprints
  - Size estimation, planning poker
- Releases and release planning
  - Burn-down charts
  - Development speed
- Roadmaps and roadmapping

---
Thank you! Questions?
dirk.riehle@fau.de – http://osr.cs.fau.de
dirk@riehle.org – http://dirkriehle.com – @dirkriehle
DR

---
Credits and License
- Original version
  - © 2021 Dirk Riehle, some rights reserved
  - Licensed under Creative Commons Attribution 4.0 International License
- Contributions
  - None yet