Project Crash Course
Prof. Dr. Dirk Riehle
Friedrich-Alexander University Erlangen-Nürnberg
AMOS B01
Licensed under CC BY 4.0 International
[Speaker Notes: It is Friedrich-Alexander University Erlangen-Nürnberg – FAU, in short. Corporate identity wants us to say “Friedrich-Alexander University”.]

---
Project Goal
To deliver useful software at the end of the project that can be developed further.

---
Software Development Process
Scrum Process Practices
XP Technical Practices

---
Scrum Roles
SM
PO
SD
Product
Owner
Scrum
Master
Software
Developer

---
Core (“Committed”) Role Responsibilities
- Definition of product owner
  - Holds overall responsibility for the product being developed
  - Provides product vision and product requirements
  - Plans and helps plan development and tracks progress
- Definition of software developer
  - Holds overall responsibility for design and implementation of product
  - Estimate complexity (“size”) of product features to be implemented
  - Organizes and allocates design and implementation tasks
- Definition of Scrum master
  - Is responsible for tracking and resolving impediments

---
Industry Partner Responsibilities
- Definition of industry partner
  - Provides high-level requirements
  - Provides feedback in defined intervals
  - Cf. Industry Guidance, see http://bit.ly/2IhUFRn

---
Overall Project Time-Line
P:	Planning
E:	Execution
3R:	Review, release, and retrospective
P
E
 3R
P
E
 3R
Sprint 1
Sprint n
time
E.g. week 1
E.g. week n
...
...
Mid-Project Release
Final Release
time
Sprints 1 to n/2
Sprints (n/2+1) to n

---
Time-boxed Sequence of Releases
- Definition of release
  - A named, identifiable, consistent, and useful snapshot of the software and related relevant artifacts
- Definition of sprint release
  - A release used to gather feedback from industry partner to help steer the project (every week)
- Definition of project release
  - A release used to deploy for production (twice during the semester: mid-term and at end of semester)

---
The Scrum Sprint (Conceptualization)
Process improvement
Product management
Software development
Daily Scrum
Retrospective
Release
Review
Process improvement
Product management
Software development
Daily Scrum
Next sprint
preparation
Process improvement
Product management
Software development
Daily Scrum
Process improvement
Product management
Software development
Sprint
planning
Wed
...
09:00
13:00
17:00
Tue
Mon
Thu

---
Project Schedule
- See Course index → Course schedule
  - For date ↔ course week mapping
- See Course deliverables slide deck
  - For deliverables due for a course week
[Speaker Notes: The main deliverables: Initial and mid-term release plan Mid-term and final release]

---
Other Role Responsibilities
- Definition of review and release manager
  - Prepares the product for review session
  - Releases the product after agreement

---
Example Product Vision [1] and Project Mission
- Wahlzeit / Flowers product vision
  - The Flowers social network helps flower enthusiasts worldwide to connect with each other and enjoy following their favorite hobby online. Centered on showing and rating favorite flower photos, it inspires growing and presenting ever more beautiful flowers. With a highly engaged user community, Flowers is the best place for producers and sellers of gardening supply to reach out to customers and engage with them. Such engagement involves understanding flower enthusiasts’ needs around gardening supplies and selling to them.
- AMOS project mission
  - The mission of the AMOS project is to enhance the Wahlzeit software with a mobile cross-plattform app, available both on Android and iPhone. To achieve this, the current domain model interface needs to be refactored into a REST-based API to be used by all user interfaces, whatever the modality.
[1]	See http://goo.gl/pOazTZ

---
Feature and User Story
- Definition of feature
  - A distinguishing characteristic of a software item (for example, performance, portability, functionality)
    (IEEE 829)
- Definition of user story
  - A description mechanism for a software feature used to create a shared understanding of the feature; follows an established pattern
  - The description pattern is: As a “user role”, I need “a function”, so that “I get business value” where the parts in quotation marks are substituted
- Example user stories
  - Rate-a-photo: As a visitor, I can rate a photo with a numerical value 1-10, so that I can share my opinion about the photo.
  - Tell-a-friend: As a user, I need a function to tell a friend about a flower photo, so that I can share my passion for flowers.

---
The Tell-a-Friend Feature

---
Quality Criteria for Feature Descriptions
I	ndependent: Features should be independent of each other.
N	egotiable: A feature is man-made, not cast in stone.
V	aluable: Every feature should have business value.
E	stimatable: A feature should be precise so that size can be estimated.
S	mall: A feature should be small enough for one iteration.
T	estable: A feature should have testable success criteria.

---
Flowers Planning Documents
See http://goo.gl/FRfym

---
Product Backlog and Product Backlog Entry
- Definition of product backlog
  - An incomplete and evolving list of features prioritized by business value and used in product planning
- Definition of product backlog entry
  - A named, identifiable, and prioritized feature or bug that is part of a product backlog

---
Flowers Product Backlog

---
Sprint Backlog and Sprint Backlog Entry
- Definition of sprint backlog
  - A list of sprint backlog entries that the software developers have committed to implementing in the current sprint
- Definition of sprint backlog entry
  - A high-quality product backlog entry that has been estimated for size and committed-to to being implemented by the software developers

---
Flowers Sprint Backlog

---
The AMOS Team Meeting
...
...
5. Sprint Planning
6. Meeting After-work
1. Meeting Preparation
3. Sprint Release
4. Sprint Retrospective
2. Sprint Review
Team Meeting Day
Previous
Sprint
Next
Sprint
Team
Meeting

---
1. Meeting Preparation
This sprint’s review and release manager
  1. Ensure that a working demo system will be available
  2. Tag release candidate with sprint-xx-release-candidate
    - where xx is your sprint number (see project schedule)
- Next sprint’s product owner
  - Ensure that product backlog is ready for sprint planning
    - Include new user stories
    - May transcribe bugs from issues
    - May include refactorings

---
2a. Sprint Review
This sprint’s review and release manager
  1. Check-out fresh code base using release candidate tag
  2. Compile, build, and run tests for release candidate
  3. Deploy release candidate to test environment

---
2b. Sprint Review
- This sprint’s product owner
  - Walk through sprint backlog feature by feature
    1. Ask developer to demo current feature
    2. Check fulfillment of acceptance criteria
    3. Check other criteria incl. logging output for problems
    4. If successfully implemented, move feature to feature archive
    5. If not successfully implemented, move feature back to product backlog
- Software developer
  1. Demo feature as requested by product manager
  2. Answer questions about feature design and implementation

---
Flowers Feature Archive

---
3. Sprint Release
- This sprint’s product owner
  - Decide whether release candidate should be released
    - Only in case of significant regression should you not release
  - Consult with software developers if necessary
- This sprint’s review and release manager
  - If the release candidate is to be released
    1. Deploy sprint release to operations environment
    2. Tag release with sprint-xx-release
      - where xx is your sprint number
  - If you maintain a work log (optional)
    - Update work log with release information

---
4. Sprint Retrospective
This sprint’s Scrum master
  - Review this sprint’s impediments
    - Report on progress
    - Review remaining problems
Next sprint’s Scrum master
  - Make roll call as to new impediments
    - Take note of people's impediments
    - Allow everyone to make a suggestion
  - Note impediments in impediments backlog
Everyone
  - Answer to happiness index

---
5. Sprint Planning
This (now new) sprint’s product owner
  1. Reprioritize backlog items, if necessary, on-the-fly
  2. Work through top-prioritized backlog items one-by-one until finished
    - For each product backlog item, explain it, ask developers to estimate and commit
    - You are finished, if the team does not want to take on more backlog items
- Software developer
  - Estimate size of each backlog item using planning poker
  - After planning, commit to backlog items put into sprint backlog
- Everyone
  - Make sure roles for sprint are clear to everyone

---
Story Points
- Story point
  - An arbitrary numeric measure of size of a given feature
- Properties
  - Is a measure of size, not of effort or duration
  - Measured in non-linear increments, forcing choice
  - Is socially agreed upon, depends on team estimation history
  - Is independent of a particular person (and their skills)
  - Is mapped to time using the team's velocity (dev. speed)
Points	Meaning
0	No effort
1	Minimal effort
2	Small effort
3	Medium effort
5	Large effort
8	Very large effort
13	Too large effort

---
Flow Diagram for Sprint Planning [1]
[1]	A simple planning poker cards replacement can be found in the planning documents
Product Owner
Picks Story
Product Owner
Reads Story
Product Owner
Explains Story
Developers
Discuss Story
Each Developer
Deliberates
Each Developer
Plays Card
Agreement?
no
Product Owner
Adjusts Backlog
Developers Re-
view Total Effort
Done?
no
yes
yes
 start
end

---
6. Meeting After-work
- This sprint’s product owner
  - Update planning documents to consistent state
    - Clean up product and sprint backlog
    - Ensure feature archive is current
    - Update release plan with actual effort for sprint
- This sprint’s Scrum master
  - Work on resolving impediments during sprint
  - Document resolutions in impediments backlog

---
Weekly Checklist for Artifacts
- Planning documents
  - Clean release plan, product backlog, sprint backlog, and feature archive
- Software product
  - Tagged, testable, deployable software code base and product
- Process improvement
  - Impediments documented, discussed; happiness index survey taken

---
Next Steps
See Course deliverables slide deck

---
Thank you! Questions?
dirk.riehle@fau.de – http://osr.cs.fau.de
dirk@riehle.org – http://dirkriehle.com – @dirkriehle
DR

---
Credits and License
- Original version
  - © 2012-2020 Dirk Riehle, some rights reserved
  - Licensed under Creative Commons Attribution 4.0 International License
- Contributions
  - ...